## Feuil1
Page Link | Task | Component | Status | Start | End | Assign | Remarks
| Create | DB-Tables | Complete | 2017-03-20 | 2017-03-20 | Nick, Eros
| Create | BE-API | Complete | 2017-03-21 | 2017-03-21 | Nick, Eros
| Update | Dep-Angular | Complete | 2017-03-27 | 2017-03-27 | Nick | Update Angular 2 to Angular 4
| Design Slice | Splash Page | assign | 2017-05-04 | 2017-05-25 | RR, Albert & LA | page, waiting for color/style guides. To be sliced by LA and Albert
| Slice |  |  |  | 42835 | Albert, LA, Gezel
| Function |  | Complete | 2017-05-25 | 2017-05-25 | Eros | For Integration
| Design Slice | Master Page | assign | 2017-05-15 |  | Albert & LA | some modification needed, Manulife is too expanded and background color of navigation is too similar. Color code for highlight (RR), logo has been provided by RR.
| Slice |  |  | 42825 | 42835 | Albert, LA, Gezel
| Function |  | Completed | 2017-04-03 | 2017-04-03 | Eros | testing image and video resource
1) MBPS DIS Overview | Resource | 01 - MBPS DIS Overview - DIS Mission Vision | Provided |  | 2017-05-08 | Sir Denmar
| Design Slice |  | Completed | 2017-05-15 | 2017-05-15 | RR, Albert & LA | Design, provided by RR. To be sliced by LA and Albert
| Slice |  | Completed | 42825 | 42825 | Albert, LA, Gezel
| Function |  | Completed | 2017-05-15 | 2017-05-19 | Eros | For Integration
| Resource | 02 - MBPS DIS Overview - Org Chart | Provided |  | 2017-05-08 | Sir Denmar
| Design Slice |  | Completed | 2017-05-09 | 2017-05-19 | RR, Albert & LA | Assign to LA, Albert
| Slice |  | Completed | 42825 | 42835 | Albert, LA, Gezel
| Function |  | Completed |  | 2017-05-19 | Eros | For Integration
| Resource | 03 - MBPS DIS Overview - Stratergies | Provided |  | 2017-05-08 | Sir Denmar
| Design Slice |  | Completed | 2017-05-15 | 2017-05-15 | RR, Albert & LA | Design, provided by RR. To be sliced by LA and Albert
| Slice |  | Completed | 42825 | 42825 | Albert, LA, Gezel
| Function |  | Completed | 2017-05-15 | 2017-05-19 | Eros | For Integration
| Resource | 04 - MBPS DIS Overview - Service Catalogue | Provided |  | 2017-05-08 | Sir Denmar
| Design Slice |  | assign | 2017-05-15 | 2017-05-19 | RR, Albert & LA | Assign to RR. To be sliced by LA and Albert
| Slice |  | Completed | 42825 | 42835 | Albert, LA, Gezel
| Function |  | Not Started |  |  | Eros | For Integration
| Resource | 05 - MBPS DIS Overview - Programs - Aspire | Pending | 2017-05-19 |  | JP | For Verification with Sir Denmar
| Design Slice |  | Not Started | 2017-05-26 | 2017-05-26 | RR, Albert & LA
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Completed | 2017-05-26 | 2017-05-26 | Eros | For Integration
| Resource | 06 - MBPS DIS Overview - Programs - Cares | Pending | 2017-05-19 |  | JP | For Verification with Sir Denmar
| Design Slice |  | Not Started | 2017-05-26 | 2017-05-26 | RR, Albert & LA
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Completed | 2017-05-26 | 2017-05-26 | Eros | For Integration
| Resource | 07 - MBPS DIS Overview - Programs - Careers | Pending | 2017-05-19 |  | JP | For Verification with Sir Denmar
| Design Slice |  | Not Started | 2017-05-26 | 2017-05-26 | RR, Albert & LA
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Completed | 2017-05-26 | 2017-05-26 | Eros | For Integration
| Resource | 08 - MBPS DIS Overview - Programs - Digerati | Pending | 2017-05-19 |  | JP | For Verification with Sir Denmar
| Design Slice |  | Not Started | 2017-05-26 | 2017-05-26 | RR, Albert & LA
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Completed | 2017-05-26 | 2017-05-26 | Eros | For Integration
| Resource | 09 - MBPS DIS Overview - Programs - Motivate | Pending | 2017-05-19 |  | JP | For Verification with Sir Denmar
| Design Slice |  | Not Started |  |  | RR, Albert & LA
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Not Started |  |  | Eros | For Integration
2) Team Overview | Resource | 10 - Team Overview - Team Org Chart | Provided |  |  | JP
| Design Slice |  | assign | 2017-05-15 |  | Albert & LA | This is different per team
| Slice |  | Completed | 42825 | 42835 | Albert, LA, Gezel
| Function |  | assign | 2017-05-19 | 2017-05-24 | Eros | Start Integrating available image given by LA/Albert and start functionality of loading images depending on the user team
| Resource | 11 - Team Overview - Job Management Program - Team Services | Provided |  |  | JP
| Design Slice |  | assign | 2017-05-15 |  | Albert & LA | This is different per team
| Slice |  | Completed | 42825 | 42835 | Albert, LA, Gezel
| Function |  | assign | 2017-05-19 | 2017-05-24 | Eros | Start Integrating available image given by LA/Albert and start functionality of loading images depending on the user team
| Resource | 12 - Team Overview - Job Management Program - Team Application/Tools | Provided |  |  | JP
| Design Slice |  | assign | 2017-05-15 |  | Albert & LA | This is different per team
| Slice |  | Completed | 42825 | 42835 | Albert, LA, Gezel
| Function |  | assign | 2017-05-19 | 2017-05-24 | Eros | Start Integrating available image given by LA/Albert and start functionality of loading images depending on the user team
| Resource | 13 - Team Overview - Job Management Program - Team Tools | Assign | 2017-05-09 |  | JP | This is different per team
| Design Slice |  | Not Started |  |  | RR, Albert & LA | This is different per team
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros | Dynamic content
3) Leader' Video | Resource | 13 - Leaders Video - AVP Video | Pending |  |  | JP | Will be provided
| Design Slice |  | Not Started |  |  | RR, Albert & LA
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Not Started |  |  | Eros | For Integration
| Resource | 14 - Leaders Video - Manager Video | Pending |  |  | JP | Will be provided
| Design Slice |  | Not Started |  |  | RR, Albert & LA | This is different per team
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Not Started |  |  | Eros | For Integration
| Resource | 15 - Leaders Video - Team Lead Video | Pending |  |  | JP | Will be provided
| Design Slice |  | Not Started |  |  | RR, Albert & LA | This is different per team
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Not Started |  |  | Eros | For Integration
4) MBPS DIS Tools | Resource | 16 - MBPS DIS Tools - OPT | Provided |  |  | JP
| Design Slice |  | N/A |  |  | RR,Albert, LA
| Slice |  | Slice | 42835 |  | Albert, LA
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros | Dynamic content
| Resource | 17 - MBPS DIS Tools - Workday | Pending | 2017-05-19 |  | JP | Document
| Design Slice |  | N/A |  |  | RR,Albert, LA
| Slice |  | Slice | 42835 |  | Albert, LA
| Function |  | Not Started |  |  | Eros | For Integration
| Resource | 18 - MBPS DIS Tools - Khronos | Provided |  |  | JP
| Design Slice |  | N/A |  |  | RR,Albert, LA
| Slice |  | Slice | 42835 |  | Albert, LA
| Function |  | Completed | 2017-04-03 | 2017-04-10 | Eros | Dynamic content
| Resource | 19 - MBPS DIS Tools - Contact Numbers | Pending |  |  | JP | Will be provided
| Design Slice |  | Not Started |  |  | RR, Albert & LA
| Slice |  |  |  |  | Albert, LA, Gezel | This wil be a link as per request
| Function |  | Not Started |  |  | Eros | For Integration
5) Policy | Resource | 19 - Policy - House Rules | Provided |  | 2017-05-08 | Sir Denmar
| Design Slice |  | N/A |  |  | RR,Albert, LA
| Slice |  | Slice | 42835 |  | Albert, LA
| Function |  | Completed |  |  | Eros
| Resource | 20 - Policy - Vacation Leave | Provided |  | 2017-05-17 | JP
| Design Slice |  | N/A |  |  | RR,Albert, LA
| Slice |  | Slice | 42835 |  | Albert, LA
| Function |  | Not Started |  | 2017-05-19 | Eros | For Integration
| Resource |  | Provided |  | 2017-05-17 | JP
| Design Slice | 21 - Policy - Bereavement | N/A |  |  | RR,Albert, LA
| Slice |  | Slice |  |  | Albert, LA
| Function |  | Not Started |  | 2017-05-19 | Eros | For Integration
6) exam | Resource | 22 - Take the Exam | Pending |  |  | JP | Provided Correct answers
| Design Slice |  | N/A |  |  | RR,Albert, LA
| Slice |  | Slice |  |  | Albert, LA
| Function |  | Pause/Waiting | 2017-05-15 |  | Eros
7)Credits | Resource | 23 - Credits | N/A |  |  | JP
| Design Slice |  | assign | 2017-05-15 |  | RR, Albert & LA | Assign to RR (Design)
| Slice |  | Completed | 42825 | 42835 | Albert, LA, Gezel
| Function |  | Not Started |  |  | Eros | For Integration